## Лист1
Questions for Rakhmetzhan
What is KZ conversion rate? How many visits? How many conversions?
Which tools to use for most effective low-cost advertising?
How much time needed?
Which domain (zakazhiedu.kz or zakazhiedu.com) should be used and why?
To Do list for Zhandos & Daniyar (web-development, design) | When?
Profile editing
Restaurant page or platform
Yandex maps or geolocation
Hosting (to be defined after meeting w/ Rahmetzhan on 03.09.2013)
Function to import data for partners (http://satu.kz/cabinet/product_import/import_review)
Website account balance possible to fill w/ cash and pay from account
Launch a website for beta testing | Nov 1st
To Do list for Oralbek (sales & financials) | When?
finish biz plan (b-plan is 80% finished, need to make financial statements, calculate break-even) | Sep 20th
make a presentation for partners | Oct 1st
To Do list for Sunkar (marketing)
write a short list of questions to survey during beta testing period